## Sheet1
Description | Task | Must Follow | Time(weeks)
Define Project scope | A | None | 1
Conduct User Research | B | A | 1
Gathering Requirements | C | A | 1
High Level Design | D | B, C | 1
Design database | E | D | 2
Design Software | F | D | 2
Design User Interface | G | D | 2
Finalice Design | H | E, F, G | 1
Develop System Modules | I | H | 4
Integrate System Modules | J | I | 1
Preform Initial Testing | K | J | 1
Complete Development | L | K | 1
Perform System Testing | M | L | 2
Document Found Issues | N | M | 1
Correct Found Issues | O | N | 2
Finalize System | P | O | 1
Total Weeks |  |  | 19
Tasks
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Time(weeks)